## General Budget
Project Activities | Assigned To | Planned Hours | Actual Hours | $/HR | Materials UNITS | $/UNITS | Travel | Equipment | Fixed Costs | Miscellaneous | Labor Cost | Materials Cost | Budgeted | Contingency 7% | Management Reserve 5% | Actual
Environment Setup | Team A | 80 | 78 | 50 | 10 | 100 | 500 | 2000 | 500 | 300 | 3900 | 1000 | 8200 | 574 | 410 | 9184
Design Platform | Team B | 100 | 102 | 45 | 15 | 80 | 600 | 1500 | 800 | 250 | 4590 | 1200 | 8940 | 625.8 | 447 | 10012.8
AI Integration | Team C | 120 | 118 | 60 | 5 | 150 | 400 | 1800 | 400 | 200 | 7080 | 750 | 10630 | 744.1 | 531.5 | 11905.6
Game Development | Team D | 200 | 195 | 55 | 20 | 120 | 700 | 2500 | 700 | 350 | 10725 | 2400 | 17375 | 1216.25 | 868.75 | 19460
Leaderboard Development | Team E | 150 | 148 | 50 | 10 | 100 | 650 | 2200 | 600 | 300 | 7400 | 1000 | 12150 | 850.5 | 607.5 | 13608
Testing and Deployment | Team F | 180 | 182 | 60 | 25 | 90 | 500 | 2000 | 550 | 400 | 10920 | 2250 | 16620 | 1163.4 | 831 | 18614.4
Documentation Creation | Team G | 90 | 88 | 40 | 5 | 50 | 300 | 1200 | 300 | 150 | 3520 | 250 | 5720 | 400.4 | 286 | 6406.4
User Registration | Team H | 75 | 74 | 45 | 8 | 70 | 400 | 1500 | 350 | 200 | 3330 | 560 | 6340 | 443.8 | 317 | 7100.8
Security Implementation | Team I | 110 | 112 | 50 | 10 | 85 | 450 | 1800 | 450 | 250 | 5600 | 850 | 9400 | 658 | 470 | 10528
Final Adjustments | Team J | 50 | 52 | 55 | 5 | 110 | 300 | 1000 | 500 | 300 | 2860 | 550 | 5510 | 385.7 | 275.5 | 6171.2